1o8Hub

Full Product Launch

Development Plan

March 27 – April 30, 2026

34 Working Days  |  5 Sprints  |  21 Features

Prepared by 1o8 Agency

Production: https://1o8hub.vercel.app

# Executive Summary

1o8Hub is an Amazon agency management platform built on Next.js 16, React 19, and PostgreSQL. Core features (products, A+ content, SEO pipeline, client portal, Amazon sync, BigQuery publish) are complete and in production.

This plan covers 21 new features across 5 weekly sprints to take the platform from an internal tool with gaps to a fully production-ready system by April 30, 2026. The scope includes AI-powered agents, PPC tracking, financial reporting, Asana integration, calendars, and daily automated audits.

| DB Tables | Integrations | Pages | API Routes |
| --- | --- | --- | --- |
| 46 | 9 external | 67 | ~100 |

# Sprint Timeline

| Sprint | Dates | Theme | Features | Effort |
| --- | --- | --- | --- | --- |
| Week 1 | Mar 27 – Apr 2 | Foundation + Gantt v2 | 4 features | 5 days |
| Week 2 | Apr 3 – Apr 9 | Financial & Inventory | 4 features | 5 days |
| Week 3 | Apr 10 – Apr 16 | PPC & Tracking | 4 features | 5 days |
| Week 4 | Apr 17 – Apr 23 | Calendars, Audits, Asana | 5 features | 5 days |
| Week 5 | Apr 24 – Apr 30 | AI Agents & Polish | 4 features | 5 days |

# Week 1: Foundation + Gantt v2

March 27 – April 2, 2026

## Feature 1: Gantt v2 Redesign

Effort: 2 days

- Calendar date headers derived from client onboardingDate + (week x 7)

- Expanded frozen columns: WBS | Task Name | Start Date | End Date | Duration | % | Status

- Phase summary bar at top with colored progress strip per section

- Files: client-gantt.tsx, gantt API routes

## Feature 2: SOW Checklist

Effort: 1 day

- New sow_checklist table (client_id_code, item, category, status, due_date, assigned_to, notes)

- Page at /clients/[id]/sow with popover editing (reuse Gantt pattern)

- Seeded from AIA/NTA templates based on client type

## Feature 3: Attribute Checks & Missing Reports

Effort: 1 day

- New /reports/attributes page querying columnAttributes requirements vs master values per client

- Show missing required/conditional fields with XLSX export

## Feature 4: Hour Reporting

Effort: 1 day

- New client_hours table (client_id_code, user_id, date, hours, category, notes)

- Page at /clients/[id]/hours with weekly/monthly summaries and team breakdown

# Week 2: Financial & Inventory

April 3 – April 9, 2026

## Feature 5: Full P&L Financial Reporting

Effort: 2 days

- Extend /finances with P&L view per client: revenue, COGS, ad spend, fees, net profit

- Pull from Redshift settlement data + sales summary cache

- PDF and XLSX export at /finances/pl

## Feature 6: End of Month Reporting

Effort: 1 day

- Auto-generate monthly client report: sales, ad spend, SEO changes, A+ status, Gantt progress

- Template at /reports/monthly/[clientIdCode] with PDF export

## Feature 7: Inventory Recommendations

Effort: 1 day

- Fix blank 30d/90d columns in salesSummaryCache via product_summary aggregation

- Add restock alert logic: current stock / daily velocity = days of supply

## Feature 8: Forecasting vs Real Sales

Effort: 1 day

- New /clients/[id]/forecast comparison view with chart overlay (projected vs actual)

- Variance % calculation and trend indicators

# Week 3: PPC & Tracking

April 10 – April 16, 2026

## Feature 9: PPC Campaign Tracker

Effort: 2 days

- Dashboard at /ppc showing campaigns, spend, ACOS, TACOS, ROAS by client

- Pull from Intentwise/Redshift PPC tables with 6-hour cron refresh

- New ppc_campaigns table for caching campaign-level metrics

## Feature 10: PPC Gap Identifier

Effort: 1 day

- Analyze keyword coverage gaps: SEO keywords not in PPC campaigns

- Identify high-spend low-conversion terms at /ppc/gaps

## Feature 11: Keyword Tracker

Effort: 1 day

- New keyword_rankings table (asin, keyword, rank, search_volume, date)

- Helium10 CSV import pipeline + daily cron refresh

- Rank history chart at /seo/keywords

## Feature 12: Price Tracker

Effort: 1 day

- New price_history table tracking price, buy box, competitor prices daily

- Price chart on product detail page + alerts for significant changes

# Week 4: Calendars, Audits & Asana

April 17 – April 23, 2026

## Feature 13: Promo Tracker + Calendar

Effort: 1.5 days

- New promotions table (client, asin, promo_type, discount, start/end dates, status)

- Calendar view at /calendar/promos using existing calendar pattern

## Feature 14: SEO Calendar

Effort: 0.5 day

- Extend /calendar with SEO milestones from seoProjects phase timestamps

## Feature 15: Variation Daily Reports

Effort: 1 day

- Daily cron comparing SP-API variation data vs Hub, storing diffs in variation_audit_log

- Dashboard at /variations/reports showing broken/changed variations

## Feature 16: SEO & Content Daily Checks

Effort: 1 day

- Daily cron comparing live Amazon content (snapshots) vs SEO-generated source of truth

- Audit report at /seo/audit with actionable fix recommendations

## Feature 17: Asana Integration

Effort: 1 day

- Asana API client at src/lib/asana.ts with full read/write support

- Sync tasks per client to /clients/[id]/tasks, map Gantt tasks to Asana

# Week 5: AI Agents & Polish

April 24 – April 30, 2026

## Feature 18: Auto-Assign Asana Tasks

Effort: 0.5 day

- When Gantt task status changes or SOW item is due, auto-create/update Asana task

## Feature 19: Claude AI Agent

Effort: 2 days

- Multi-mode AI agent at /api/ai/agent:

- (a) Case study generator — pull client metrics, generate narrative

- (b) Data audit — pack size, price point, missing attributes

- (c) PPC audit — campaign efficiency, wasted spend analysis

- (d) Amazon strategy — market recommendations per client

## Feature 20: Potential Client Audit

Effort: 1 day

- New /prospects page: input competitor ASIN/brand, Rainforest scrape, Claude analysis

- Output: market size, gaps, opportunity score stored in prospect_audits table

## Feature 21: Final Polish & Testing

Effort: 1.5 days

- Fix open blockers: Resend DNS verification, Intentwise health report

- End-to-end testing of all 20 new features

- Portal verification for client role users, production deploy

# New Database Tables

12 new tables will be added to the PostgreSQL schema via Drizzle migrations.

| Table | Key Columns |
| --- | --- |
| sow_checklist | client_id_code, item, category, status, due_date, assigned_to, notes |
| client_hours | client_id_code, user_id, date, hours, category, notes |
| ppc_campaigns | client_id_code, campaign_id, name, type, status, budget, spend_mtd, acos, roas |
| keyword_rankings | asin, keyword, rank, search_volume, date, source |
| price_history | asin, price, buy_box_price, competitor_price, date |
| promotions | client_id_code, asin, promo_type, discount_pct, start_date, end_date, status |
| variation_audit_log | asin, field_name, old_value, new_value, detected_at, resolved |
| content_audit_log | asin, field_name, expected_value, live_value, detected_at, status |
| prospect_audits | brand_or_asin, audit_data (JSONB), opportunity_score, created_by, created_at |
| asana_task_links | gantt_task_id, asana_task_id, asana_project_id, synced_at |

## New Cron Jobs

| Route | Frequency | Purpose |
| --- | --- | --- |
| /api/cron/ppc-refresh | Every 6h | Pull PPC campaign data from Redshift |
| /api/cron/variation-audit | Daily | Compare SP-API variation data vs Hub |
| /api/cron/content-audit | Daily | Compare live Amazon content vs SEO source of truth |
| /api/cron/keyword-rank | Daily | Pull keyword ranking data from Helium10 |

# External Dependencies

| Dependency | Status | Action Needed |
| --- | --- | --- |
| Asana API | Ready | User will provide API key + project IDs. Full integration from day 1 |
| Intentwise/Redshift | Available | PPC campaign data flows through Intentwise. Query existing tables |
| Helium10 | TBD | Need API key or CSV export integration. Build import pipeline |
| Resend DNS | Blocked | User must complete DNS verification for 1o8.agency domain |

# Risk Assessment

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Helium10 API access unknown | Medium | Start with CSV import; add API later |
| Redshift PPC schema unknown | Medium | Query schema first day of Week 3 to confirm tables |
| 34 days for 21 features | High | Prioritize by business value; cut AI agent scope if needed |
| Asana project structure unknown | Low | Get project IDs from user during Week 4 setup |

# Priority Tiers

If time runs short, features are prioritized in three tiers:

### Must Ship (Weeks 1–3)

- Gantt v2, P&L Financial Reporting, Attribute Reports

- Inventory Fix, PPC Tracker, SOW Checklist, Hour Reporting

### Should Ship (Week 4)

- Promo Calendar, SEO Calendar, Variation Daily Reports

- SEO Content Daily Checks, Asana Integration, Keyword Tracker

### Nice to Have (Week 5)

- Claude AI Agent (case studies, data audit, PPC audit, strategy)

- Potential Client Audit, Auto-Assign Asana Tasks

# Verification Protocol

After each weekly sprint:

- npm run build — must pass with zero errors

- npm run lint — clean output

- Manual QA of each new page

- Deploy to Vercel, verify on production

- Portal spot-check for client role users

End of Plan